## Checklist
Section | Item | Status | Owner | ETA | Notes | Evidence
Core Infrastructure | Monorepo build succeeds | ❌ FAIL | Platform | 2025-10-29 | API build misses TypeScript lib stubs; web build cannot locate Next.js binary. | logs/audit_2025-10-27_api_build.log:35 — TS6053 missing lib.es2022.d.ts logs/audit_2025-10-27_web_build.log:27 — Error: Cannot find module 'next/dist/bin/next'
Core Infrastructure | Workspace lint passes | ❌ FAIL | Platform | 2025-10-29 | ESLint binary not reachable from run-cli shim for both API and web packages. | logs/audit_2025-10-27_api_lint.log:19 — MODULE_NOT_FOUND for eslint/bin/eslint.js logs/audit_2025-10-27_web_lint.log:19 — MODULE_NOT_FOUND for eslint/bin/eslint.js
Core Infrastructure | Type-check clean | ❌ FAIL | Platform | 2025-10-29 | TypeScript standard library d.ts bundles absent from node_modules across API and web. | logs/audit_2025-10-27_api_typecheck.log:11 — TS6053 missing lib.dom.d.ts / lib.es2022.d.ts logs/audit_2025-10-27_web_typecheck.log:11 — TS6053 missing lib.dom/iterable/esnext d.ts
Core Infrastructure | Docker compose aligned with repo | ❌ FAIL | Platform | 2025-10-31 | Compose file still points at historical ./backend and Neon-v2.4.0/ui contexts that do not exist in this monorepo. | docker-compose.yml:24 — backend build context set to ./backend docker-compose.yml:45 — ui build context set to ./Neon-v2.4.0/ui
Core Infrastructure | CI workflows configured & reproducible | ⚠️ WARNING | DevOps | 2025-11-04 | Workflow definitions exist but depend on pnpm commands that currently fail locally due to missing toolchain binaries. | .github/workflows/ci.yml:21-42 — pipeline expects pnpm build/type-check/tests logs/audit_2025-10-27_api_build.log:35 — local parity failure replicates the same toolchain gap
DB & Data | Prisma schema complete | ✅ PASS | Data | Complete | Schema covers agents, RAG, telemetry, and declares pgvector extension. | apps/api/prisma/schema.prisma:1-40 — datasource enables vector extension apps/api/prisma/schema.prisma:569-633 — Chunk/ModelVersion/TrainingJob definitions
DB & Data | Prisma migrate status clean | ⚠️ WARNING | Data | 2025-10-30 | Running migrate status fails before reaching the database because the Prisma CLI binary cannot execute without the missing TypeScript stdlib files. | logs/audit_2025-10-27_prisma_status.log:3-12 — prisma build/index.js aborts before reporting status
DB & Data | pgvector operational | ⚠️ WARNING | Data | 2025-11-05 | Schema and health check query vector extension, but no runtime verification was possible because the API build is broken. | apps/api/prisma/schema.prisma:14-22 — datasource extensions include vector apps/api/src/routes/health.ts:49-70 — health check queries pg_extension for 'vector'
DB & Data | Seed data covers baseline | ⚠️ WARNING | Data | 2025-11-01 | Seed script provisions org/agents/connectors but has not been executed in this environment; relies on Prisma client availability and DB connectivity. | apps/api/prisma/seed.ts:1-210 — creates org, roles, embedding space, connectors
DB & Data | Critical indexes in place | ⚠️ WARNING | Data | 2025-11-06 | Several @@index declarations exist yet high-traffic tables like Conversation/AgentRun lack dedicated latency indexes; requires review once migrations can run. | apps/api/prisma/schema.prisma:387-520 — limited @@index coverage on agent tables
DB & Data | Backups & Neon branching | ⚠️ WARNING | Data | 2025-11-08 | Playbooks capture process but no automation evidence captured during audit; requires validation once database connectivity is restored. | docs/DB_BACKUP_RESTORE.md:1-32 — documented procedure without execution logs
AI Agents | Agents exposed via tRPC | ❌ FAIL | AI | 2025-11-07 | UI hook still stubs tRPC client and falls back to REST placeholders; no generated procedures. | apps/web/src/hooks/useCopilotRouter.ts:8-24 — comment notes tRPC client missing
AI Agents | Agent latency <2s (local) | ⚠️ WARNING | AI | 2025-11-12 | No latency measurements collected because orchestrator could not be exercised while builds are broken. | logs/audit_2025-10-27_api_build.log:35 — blocking build failure prevented smoke runs
AI Agents | AgentRun / AgentMetric logging | ❌ FAIL | AI | 2025-11-07 | Orchestrator registry only stores agents in memory; no writes to AgentRun/AgentRunMetric tables. | apps/api/src/services/orchestration/index.ts:5-48 — orchestrator uses in-memory registry with no persistence
Frontend & Chat | Realtime chat transport | ⚠️ WARNING | Frontend | 2025-11-05 | Socket.IO wiring exists for migration/deployment rooms, but we did not validate live traffic due to backend build failures. | apps/api/src/ws/index.ts:4-90 — socket channel subscriptions apps/web/src/hooks/useMigrationStatus.ts:24-166 — client hook for websocket
Frontend & Chat | Typing indicators | ❌ FAIL | Frontend | 2025-11-14 | BrandVoice Copilot chat renders messages without any typing state or live feedback. | apps/web/src/components/brand-voice/BrandVoiceCopilot.tsx:33-120 — no typing indicator state
Frontend & Chat | ARIA/keyboard coverage | ⚠️ WARNING | Frontend | 2025-11-18 | Navigation includes aria-current but most interactive components lack keyboard affordances; requires audit post build fix. | apps/web/src/components/navigation.tsx:62-86 — limited aria usage
Frontend & Chat | Theme toggle available | ❌ FAIL | Frontend | 2025-11-10 | ThemeProvider stores mode but AppShell exposes no toggle control for users. | apps/web/src/components/AppShell.tsx:7-47 — header lacks theme controls apps/web/src/components/theme-provider.tsx:20-58 — client context without UI
Email & CRM | SMTP / transactional email | ⚠️ WARNING | Growth | 2025-11-06 | Team invites rely on Resend and fall back to mock mode when RESEND_API_KEY is absent; no direct SMTP transport configured in runtime. | apps/api/src/services/team/invite.ts:9-72 — warns when RESEND_API_KEY missing and uses mock
Email & CRM | Template compilation | ⚠️ WARNING | Growth | 2025-11-13 | Templates are embedded strings with no build step or linting; requires templating integration for multi-variant campaigns. | apps/api/src/services/team/invite.ts:80-131 — HTML string literal template
Email & CRM | A/B testing logic | ⚠️ WARNING | Growth | 2025-11-12 | EmailAgent persists A/B test records but instrumentation can't be validated until Prisma client issues resolved. | apps/api/src/agents/EmailAgent.ts:232-315 — runABTest implementation writing prisma.aBTest
Email & CRM | Email metric logging | ⚠️ WARNING | Growth | 2025-11-18 | Metrics endpoint exists but no live events were produced during audit due to API not running. | apps/api/src/routes/metrics.ts:1-88 — event tracking route
Email & CRM | CRM sync | ⚠️ WARNING | Growth | 2025-11-20 | HubSpot connector implements OAuth actions yet depends on encrypted credentials and API connectivity that can't be exercised without the platform booting. | apps/api/src/connectors/services/HubSpotConnector.ts:1-108 — create/search contact actions
SEO & Analytics | SEO agent outputs | ⚠️ WARNING | Growth | 2025-11-15 | SEOAgent returns stubbed recommendations; requires integration with real audits. | apps/api/src/agents/SEOAgent.ts:20-63 — mock data for optimization & keywords
SEO & Analytics | Keyword index maintained | ❌ FAIL | Growth | 2025-11-22 | No keyword tables or services found in schema or codebase. | apps/api/prisma/schema.prisma — no keyword model present (rg 'keyword' returns none)
SEO & Analytics | Sitemap generated | ❌ FAIL | Growth | 2025-11-10 | robots.txt references production sitemap URL but repo lacks sitemap generation in public assets. | apps/web/public/robots.txt:1-18 — sitemap points to external URL apps/web/public — no sitemap.xml asset present
SEO & Analytics | Google Search Console integration | ❌ FAIL | Growth | 2025-11-25 | No runtime integration; documentation explicitly calls out missing GSC support. | reports/seo-agent-validation-report.md:534 — notes lack of Google Search Console
SEO & Analytics | Lighthouse ≥90 | ⚠️ WARNING | Growth | 2025-11-18 | Unable to execute Lighthouse suite because Next.js build currently fails. | logs/audit_2025-10-27_web_build.log:27 — Next.js binary missing
Neural Memory | Embeddings flow operational | ⚠️ WARNING | AI/ML | 2025-11-19 | Learning service routes events into predictive engine but cannot be verified without running API. | apps/api/src/services/learning/index.ts:1-37 — learnFrom delegates to predictive engine
Neural Memory | RAG latency <1s | ⚠️ WARNING | AI/ML | 2025-11-28 | No latency sampling collected; dependent on restoring agent execution. | apps/api/src/services/orchestration/router.ts:23-93 — execution pipeline awaiting agent handlers
Neural Memory | TrainingJob ↔ ModelVersion linkage | ❌ FAIL | AI/ML | 2025-12-03 | Schema defines relationships but application layer never writes TrainingJob records. | apps/api/prisma/schema.prisma:599-633 — TrainingJob model exists (rg) apps/api/src — no references to TrainingJob
Neural Memory | Auto-evaluation loop | ❌ FAIL | AI/ML | 2025-12-06 | No automated evaluation or scoring routines surfaced during code search. | Repository search — no auto-eval or evaluation pipeline implementations present
Neural Memory | Notion export hooks | ⚠️ WARNING | AI/ML | 2025-11-26 | Notion connector supports page creation and triggers, yet integration with memory sync is not wired. | apps/api/src/connectors/services/NotionConnector.ts:41-118 — connector capabilities
Security & Governance | RBAC roles enforced | ⚠️ WARNING | Security | 2025-11-11 | Schema models org roles but middleware primarily gates via IP allowlists; role checks absent on most routes. | apps/api/prisma/schema.prisma:121-208 — OrganizationRole definitions apps/api/src/server.ts:65-110 — admin routes rely on adminIPGuard but not role checks
Security & Governance | Audit log coverage | ✅ PASS | Security | Complete | Audit middleware captures successful operations with user/IP metadata. | apps/api/src/middleware/auditLog.ts:1-39 — audit() invoked on response apps/api/src/lib/audit.ts:1-39 — writes to prisma.auditLog
Security & Governance | API key hashing | ❌ FAIL | Security | 2025-10-30 | Encryption helper throws unless ENCRYPTION_KEY is provided; reversible encryption instead of hashing. | apps/api/src/lib/encryption.ts:5-33 — hard requirement on ENCRYPTION_KEY and AES-256-GCM
Security & Governance | CORS & rate limits | ✅ PASS | Security | Complete | Strict origin matching and dual-scope rate limiting active by default. | apps/api/src/middleware/cors.ts:1-84 — strictCORS implementation apps/api/src/middleware/rateLimit.ts:1-84 — IP/user scoped throttling
Security & Governance | Error boundaries | ⚠️ WARNING | Security | 2025-11-09 | API wraps errors with AppError but frontend boundary is basic; should add user guidance and telemetry once app builds. | apps/api/src/server.ts:86-126 — central error handler apps/web/src/components/error-boundary.tsx:1-12 — minimal fallback
Automation & CI | GH Actions green | ❌ FAIL | DevOps | 2025-10-31 | Local build/test parity fails; same issues would break required CI jobs. | logs/audit_2025-10-27_api_build.log:35 — build failure mirrors CI logs/audit_2025-10-27_api_test.log:6 — tests fail without typescript module
Automation & CI | Slack alerts wired | ❌ FAIL | DevOps | 2025-11-08 | No Slack notifications in active workflows; only referenced in historical documentation. | scripts/ci-cd — contains automated-testing, qa trigger, rollback guard only (no Slack script) reports/WORKFLOW_STATUS_DASHBOARD.md:400 — Slack action referenced as documentation
Automation & CI | Semver tagging | ✅ PASS | DevOps | Complete | Release workflow responds to v* tags with validation/build/release steps. | .github/workflows/release.yml:1-120 — tag-driven release pipeline
Automation & CI | Nightly benchmarks | ⚠️ WARNING | DevOps | 2025-11-15 | QA Sentinel workflow scheduled but runs stub CLI that generates placeholder reports. | .github/workflows/qa-sentinel.yml:23-118 — cron schedule with benchmark job core/qa-sentinel/scripts/stub-ci.js:4-48 — stub implementation
Deploy & Monitoring | Vercel/Render reachability | ⚠️ WARNING | DevOps | 2025-11-04 | Deployment descriptors exist, yet no live verification executed during audit. | render.yaml:1-24 — Render service config vercel.json:1-20 — Next.js deploy settings
Deploy & Monitoring | API health endpoint | ⚠️ WARNING | DevOps | 2025-11-02 | Health route includes database/vector/agent checks but endpoint was not reachable without successful build. | apps/api/src/routes/health.ts:1-92 — detailed health checks
Deploy & Monitoring | DB metrics visibility | ⚠️ WARNING | DevOps | 2025-11-10 | Metrics endpoint ready to broadcast but blocked by API startup failures. | apps/api/src/routes/metrics.ts:1-124 — REST analytics
Deploy & Monitoring | Logs & tracing | ⚠️ WARNING | DevOps | 2025-11-12 | Sentry integration optional and disabled without DSN; no Logtail integration found. | apps/api/src/obs/sentry.ts:5-27 — initialization short-circuits without DSN
Deploy & Monitoring | Sentry/Logtail hooked | ⚠️ WARNING | DevOps | 2025-11-12 | Only Sentry stub present; Logtail pipelines absent. | apps/api/src/obs/sentry.ts:5-27 — Sentry only
Docs & Tests | README / dev guide up to date | ⚠️ WARNING | Docs | 2025-11-05 | README still highlights v3.0 production state; needs refresh once audit artifacts added. | README.md:1-32 — references v3.0 deployment
Docs & Tests | Unit coverage ≥70% | ❌ FAIL | QA | 2025-11-08 | API test suite fails immediately because ts-jest cannot load TypeScript module. | logs/audit_2025-10-27_api_test.log:6 — Cannot find module 'typescript'
Docs & Tests | E2E suite green | ❌ FAIL | QA | 2025-11-12 | Web workspace has no configured tests; command exits after echo. | logs/audit_2025-10-27_web_test.log:3 — 'No tests configured'
Docs & Tests | Benchmarks available | ⚠️ WARNING | QA | 2025-11-20 | QA Sentinel benchmark job generates stub reports only. | core/qa-sentinel/scripts/stub-ci.js:4-48 — stubbed benchmark handler
Enhancements | Stripe billing | ⚠️ WARNING | Product | 2025-11-16 | Billing service integrates Stripe APIs but short-circuits without STRIPE_SECRET_KEY configured. | apps/api/src/services/billing/stripe.ts:1-108 — warns when STRIPE_SECRET_KEY missing
Enhancements | OAuth credential vault | ❌ FAIL | Product | 2025-11-03 | Credential encryption helper throws early without ENCRYPTION_KEY; prevents API from booting in audit environment. | apps/api/src/lib/encryption.ts:5-20 — throws if ENCRYPTION_KEY absent
Enhancements | Geo map surfaced | ❌ FAIL | Product | 2025-12-01 | No geospatial components or map integrations present in web routes. | apps/web/src/app — no geo or map modules detected (rg 'mapbox'/'leaflet' returned none)
Enhancements | Performance Copilot | ❌ FAIL | Product | 2025-12-05 | No Performance Copilot UI or API endpoints found; feature absent in current codebase. | Repository search — no 'Performance Copilot' implementations